## sprint_2
project_id | sprint_number | sprint_name | sprint_start | sprint_end | ticket_id | title | description | type | status | priority | story_points | assignee | reporter | labels | components | aws_services | epic_link | ground_truth_theme | estimated_monthly_impact_usd | created_at
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-201 | Continue Graviton migration: payments-prod canary at 50 percent | Follow-on to FIN-110. Move payments-prod canary from 5 to 50 percent on m7g.large. Validate p99 stays under 180 ms. | Story | In Progress | High | 5 | j.alvarez@example.com | k.menon@example.com | finops¦graviton¦rightsizing | payments | EC2¦EKS | FIN-EPIC-COST-25 | rightsizing | -8400 | 2026-01-22
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-202 | Buy 3-year RI for stable RDS Aurora workloads | Three Aurora clusters have 12+ months of stable utilization. Purchase 3-year, no-upfront RIs. Reviewed with finance. | Task | To Do | High | 3 | k.menon@example.com | k.menon@example.com | finops¦ri¦rds | data-platform | RDS Aurora | FIN-EPIC-COST-25 | cost_optimization | -18000 | 2026-01-22
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-203 | Decommission staging-eks-blue (replaced by green) | staging-eks-blue is replaced by staging-eks-green for two months. Drain remaining test workloads, snapshot persistent volumes, tear down. | Task | To Do | Medium | 3 | r.patel@example.com | k.menon@example.com | finops¦cleanup¦eks | platform | EKS | FIN-EPIC-COST-25 | cleanup | -3200 | 2026-01-22
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-204 | S3 Intelligent-Tiering for analytics bucket | s3://corp-analytics-prod (28 TB) has unpredictable access. Move to Intelligent-Tiering with deep archive enabled. | Story | To Do | Medium | 3 | n.oduya@example.com | k.menon@example.com | finops¦s3¦efficiency | data-platform | S3 | FIN-EPIC-COST-25 | efficiency | -2700 | 2026-01-22
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-205 | Lambda rightsize for image-resize service (drop 1024 -> 512) | image-resize p95 RAM 220 MB on 1024 MB. Drop to 512 MB. | Task | To Do | Low | 1 | s.huang@example.com | k.menon@example.com | finops¦rightsizing¦lambda | media | Lambda | FIN-EPIC-COST-25 | rightsizing | -480 | 2026-01-22
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-206 | Adopt VPC Gateway Endpoints for S3 / DynamoDB to cut NAT egress | NAT Gateway data processing charges driven heavily by S3/DynamoDB traffic. Add Gateway Endpoints in 9 VPCs. | Story | To Do | Medium | 5 | s.huang@example.com | k.menon@example.com | finops¦networking¦efficiency | networking | VPC¦S3¦DynamoDB | FIN-EPIC-COST-25 | efficiency | -6900 | 2026-01-22
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-207 | Decommission idle Redshift cluster analytics-archive | analytics-archive has been pause-eligible for 60 days. Final export to S3 Parquet, then delete. | Task | To Do | Medium | 3 | r.patel@example.com | k.menon@example.com | finops¦cleanup¦redshift | data-platform | Redshift¦S3 | FIN-EPIC-COST-25 | cleanup | -7400 | 2026-01-22
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-208 | Scale EKS payments-prod node group +40 percent for promo event | Marketing promo event 14 Feb expected 4x baseline traffic. Scale payments-prod node group from 50 to 70 m5.4xlarge. | Story | In Progress | High | 5 | j.alvarez@example.com | p.lopez@example.com | scaling¦capacity¦eks | payments | EKS¦EC2 | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 28000 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-209 | Add 2 Aurora read replicas for checkout-prod | Pre-emptive capacity for promo event. Add two r6g.2xlarge readers to checkout-prod cluster. | Story | To Do | High | 3 | s.huang@example.com | p.lopez@example.com | scaling¦capacity¦aurora | checkout | RDS Aurora | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 9600 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-210 | Add 4 Kafka brokers to events-prod cluster (capacity) | events-prod cluster MSK at 78 percent of broker CPU during peak. Add 4 brokers (m5.large) and rebalance partitions. | Story | To Do | High | 8 | j.alvarez@example.com | p.lopez@example.com | scaling¦kafka¦capacity | events | MSK | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 7200 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-211 | New feature: BNPL checkout option (Klarna) | Add Klarna BNPL flow to checkout. Includes new Lambda for tokenization, DynamoDB table, Step Functions state machine. | Story | To Do | High | 13 | p.lopez@example.com | product@example.com | feature¦checkout | checkout | Lambda¦DynamoDB¦Step Functions | GROWTH-EPIC-2026-Q1 | feature_development | 1800 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-212 | New feature: gift cards (engineering work) | Net-new gift cards module: API, DynamoDB table, fulfillment workflow. | Story | To Do | High | 13 | p.lopez@example.com | product@example.com | feature¦checkout | checkout | Lambda¦DynamoDB¦API Gateway | GROWTH-EPIC-2026-Q1 | feature_development | 2100 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-213 | Expand search to include EU region (Frankfurt) | Stand up OpenSearch + ingestion pipeline in eu-central-1 for EU users. | Epic | To Do | High | 13 | r.patel@example.com | p.lopez@example.com | expansion¦geo¦search | search | OpenSearch¦Kinesis | GROWTH-EPIC-2026-Q1 | expansion | 22000 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-214 | Pre-warm ElastiCache nodes ahead of promo | Add 2 cache.r6g.xlarge nodes to prod ElastiCache for promo. Will scale back after. | Task | To Do | High | 3 | s.huang@example.com | p.lopez@example.com | scaling¦capacity¦cache | platform | ElastiCache | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 1700 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-215 | Add per-tenant quota service (new microservice) | Net-new quota microservice (Go, EKS, DynamoDB) to enforce per-tenant rate limits. | Story | To Do | Medium | 13 | p.lopez@example.com | product@example.com | feature¦platform | platform | EKS¦DynamoDB | GROWTH-EPIC-2026-Q1 | feature_development | 1400 | 2026-01-23
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-216 | Cleanup: delete dev S3 buckets older than 180 days | 47 dev S3 buckets last modified >180 days ago, ~6 TB total. Two-step deletion (lifecycle policy + final delete) with owner notification. | Task | To Do | Low | 3 | n.oduya@example.com | k.menon@example.com | finops¦cleanup¦s3 | data-platform | S3 | FIN-EPIC-COST-25 | cleanup | -1300 | 2026-01-24
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-217 | Migrate logging from CloudWatch Logs to S3 + Athena | CloudWatch Logs ingest dominant cost line. Move structured app logs to S3 (Firehose) and query via Athena. | Story | To Do | Medium | 8 | n.oduya@example.com | k.menon@example.com | finops¦efficiency¦observability | observability | CloudWatch¦S3¦Firehose¦Athena | FIN-EPIC-COST-25 | cost_optimization | -11000 | 2026-01-24
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-218 | Bug: Karpenter not scaling down ARM nodes after Graviton rollout | After FIN-110 rollout, Karpenter consolidation does not pack ARM nodes correctly. Tune nodepool weights. | Bug | To Do | High | 3 | j.alvarez@example.com | j.alvarez@example.com | bug¦eks¦finops | platform | EKS¦EC2 | FIN-EPIC-COST-25 | bug_fixes | -2200 | 2026-01-24
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-219 | Increase ALB capacity units for promo traffic | Pre-provision LCUs on payments + checkout ALBs to absorb 4x burst. | Task | To Do | High | 2 | j.alvarez@example.com | p.lopez@example.com | scaling¦capacity¦alb | networking | ALB¦ELB | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 1100 | 2026-01-24
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-220 | Patch CVE-2026-1023 in nginx sidecar | Critical CVE in nginx sidecar; rebuild base image and roll the fleet. | Bug | In Progress | Highest | 3 | a.kim@example.com | secops@example.com | security¦cve | platform | ECR¦EKS | SEC-EPIC-2026-Q1 | security | 0 | 2026-01-21
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-221 | Reliability: add multi-AZ failover drill for payments | Run game day for payments-prod multi-AZ failover; document recovery time. | Task | To Do | Medium | 5 | a.kim@example.com | j.alvarez@example.com | reliability¦gameday | payments | EC2¦RDS |  | reliability | 0 | 2026-01-24
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-222 | Bug: cost dashboard shows EU-region as us-east-1 | Region label mapping bug after FIN-126. Fix mapping table. | Bug | To Do | Low | 1 | n.oduya@example.com | k.menon@example.com | bug¦observability¦finops | observability | QuickSight | FIN-EPIC-COST-25 | bug_fixes | 0 | 2026-01-24
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-223 | Spike: pricing model for new EU expansion | Build a sizing+pricing model for EU expansion (FIN-213). Compare 2-AZ vs 3-AZ, OpenSearch vs Aurora ES. | Spike | To Do | Medium | 3 | k.menon@example.com | p.lopez@example.com | expansion¦spike | search | OpenSearch¦RDS Aurora | GROWTH-EPIC-2026-Q1 | expansion | 0 | 2026-01-24
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-224 | Maintenance: upgrade EKS control plane to 1.30 | Routine EKS minor upgrade across 6 clusters. | Task | To Do | Medium | 5 | j.alvarez@example.com | j.alvarez@example.com | maintenance¦eks | platform | EKS |  | maintenance | 0 | 2026-01-25
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-225 | Observability: Karpenter consolidation events to Datadog | Surface Karpenter consolidation events as Datadog metrics so we can watch the FinOps impact in real time. | Story | To Do | Low | 3 | n.oduya@example.com | k.menon@example.com | observability¦finops | observability | EKS¦CloudWatch | FIN-EPIC-COST-25 | observability | 0 | 2026-01-25
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-226 | Increase DynamoDB provisioned capacity on orders-prod | Bump provisioned WCU on orders-prod from 1500 to 2400 ahead of promo. Will revisit after. | Task | To Do | High | 2 | s.huang@example.com | p.lopez@example.com | scaling¦capacity¦dynamodb | orders | DynamoDB | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 4200 | 2026-01-25
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-227 | Cleanup: legacy ECS service order-router-v1 | order-router-v1 fully replaced by v2 last sprint. Tear down ECS service, ALB target group, ECR images. | Task | To Do | Medium | 3 | r.patel@example.com | k.menon@example.com | finops¦cleanup¦ecs | orders | ECS¦ALB¦ECR | FIN-EPIC-COST-25 | cleanup | -2600 | 2026-01-25
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-228 | Add WAF rate-limit rules ahead of promo | Tighten WAF rate-limit per-IP and per-tenant in anticipation of promo abuse. | Task | To Do | High | 3 | a.kim@example.com | secops@example.com | security¦waf | edge | WAF¦CloudFront | SEC-EPIC-2026-Q1 | security | 50 | 2026-01-25
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-229 | Reliability: increase RDS backup window for checkout | Move checkout-prod backup window outside peak; lengthen retention to 14 days. | Task | To Do | Medium | 2 | s.huang@example.com | j.alvarez@example.com | reliability¦rds | checkout | RDS |  | reliability | 220 | 2026-01-25
AWS-COST-OPT-2026 | 2 | Sprint 2 - Mixed Capacity & Cost | 2026-01-26 | 2026-02-06 | FIN-230 | Refactor: extract shared SDK for cost-tagging | Extract tag-helper code (used by 14 services) into shared internal SDK to keep tagging consistent. | Story | To Do | Low | 5 | n.oduya@example.com | k.menon@example.com | finops¦refactor | platform |  | FIN-EPIC-COST-25 | efficiency | 0 | 2026-01-25