## sprint_1
project_id | sprint_number | sprint_name | sprint_start | sprint_end | ticket_id | title | description | type | status | priority | story_points | assignee | reporter | labels | components | aws_services | epic_link | ground_truth_theme | estimated_monthly_impact_usd | created_at
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-101 | Rightsize over-provisioned EC2 fleet in payments-prod | Audit shows m5.4xlarge nodes in payments-prod averaging 18 percent CPU over 30 days. Downsize to m5.2xlarge in two waves, confirm p99 latency unchanged, then commit the change in Terraform. | Story | In Progress | High | 5 | r.patel@example.com | k.menon@example.com | finops¦rightsizing¦ec2 | payments | EC2 | FIN-EPIC-COST-25 | rightsizing | -22000 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-102 | Purchase 1-year Compute Savings Plan for stable EKS baseline | Last 90 days show a stable 320 vCPU baseline across the platform-prod EKS cluster. Buy a 1-year no-upfront Compute Savings Plan to cover that baseline; everything above stays on-demand. | Task | To Do | High | 3 | k.menon@example.com | k.menon@example.com | finops¦savings-plan | platform | EC2¦Savings Plans | FIN-EPIC-COST-25 | cost_optimization | -31000 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-103 | Decommission idle RDS instance reporting-legacy-db | Reporting-legacy-db has had zero connections for 47 days and the dependent service was retired in Q4. Snapshot to S3 Glacier, validate snapshot, then delete the instance. | Task | To Do | Medium | 2 | s.huang@example.com | k.menon@example.com | finops¦cleanup¦rds | data-platform | RDS¦S3 | FIN-EPIC-COST-25 | cleanup | -1800 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-104 | Delete 3.2 TB of unattached EBS volumes flagged by Trusted Advisor | Trusted Advisor lists 412 unattached EBS volumes older than 30 days. Cross-check against the asset inventory, snapshot the ones with PII, and delete the rest in batches of 50. | Task | To Do | Medium | 3 | r.patel@example.com | k.menon@example.com | finops¦cleanup¦ebs | platform | EBS | FIN-EPIC-COST-25 | cleanup | -2400 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-105 | Apply S3 lifecycle policy to move logs to Glacier after 30 days | Application logs in s3://corp-app-logs grow ~1.4 TB per month and are queried <1 percent after 14 days. Apply lifecycle rule: Standard -> IA at 14 days, Glacier at 30 days. | Story | In Progress | Medium | 3 | n.oduya@example.com | k.menon@example.com | finops¦s3¦lifecycle | observability | S3 | FIN-EPIC-COST-25 | efficiency | -4200 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-106 | Right-size Aurora reader pool in checkout-prod | Aurora reader pool has 5 r6g.2xlarge readers averaging 11 percent CPU. Reduce to 3 readers and validate replica lag stays under 200 ms during peak. | Story | To Do | High | 5 | s.huang@example.com | k.menon@example.com | finops¦rightsizing¦aurora | checkout | RDS Aurora | FIN-EPIC-COST-25 | rightsizing | -9600 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-107 | Convert nightly batch jobs from on-demand to Spot | Nightly ETL workers currently run on on-demand m5.xlarge. Move to Spot via EKS managed node group with on-demand fallback. Idempotent jobs, retries already in place. | Story | To Do | Medium | 8 | j.alvarez@example.com | k.menon@example.com | finops¦spot¦batch | data-platform | EC2¦EKS | FIN-EPIC-COST-25 | cost_optimization | -7800 | 2026-01-10
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-108 | Tag all untagged resources with cost-center and owner | CUR shows 14 percent of monthly spend on resources without cost-center / owner tags. Roll out IAM SCP to deny untagged resource creation, then backfill tags via inventory job. | Task | To Do | Medium | 5 | n.oduya@example.com | k.menon@example.com | finops¦tagging¦governance | platform | IAM¦Cost Explorer | FIN-EPIC-COST-25 | efficiency | -1500 | 2026-01-10
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-109 | Decommission deprecated Elasticsearch domain search-v1 | search-v1 was replaced by search-v2 last quarter but still runs at 6 nodes. Confirm no inbound traffic for 30 days, snapshot, then tear down via Terraform. | Task | To Do | Medium | 3 | r.patel@example.com | j.alvarez@example.com | finops¦cleanup¦opensearch | search | OpenSearch | FIN-EPIC-COST-25 | cleanup | -5400 | 2026-01-10
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-110 | Adopt Graviton (m7g) for stateless API tier | Benchmark stateless API tier on Graviton m7g.large; ARM-compatible base image already exists. Roll out canary at 5 percent, then 50 percent, then 100 percent if p99 latency holds. | Story | To Do | High | 8 | j.alvarez@example.com | k.menon@example.com | finops¦graviton¦rightsizing | api-gateway | EC2¦EKS | FIN-EPIC-COST-25 | rightsizing | -14000 | 2026-01-10
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-111 | Reduce CloudWatch log retention from 365 to 90 days | Default log retention across 217 log groups is 365 days. Compliance requires 90. Update via AWS Config rule and remediate. | Task | To Do | Low | 2 | n.oduya@example.com | k.menon@example.com | finops¦cleanup¦cloudwatch | observability | CloudWatch¦AWS Config | FIN-EPIC-COST-25 | cleanup | -2100 | 2026-01-10
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-112 | Consolidate duplicate NAT Gateways across dev VPCs | Six dev VPCs each run their own NAT Gateway at ~$32/month plus data charges. Consolidate to a shared egress VPC via Transit Gateway. | Story | To Do | Medium | 5 | s.huang@example.com | k.menon@example.com | finops¦networking¦cleanup | networking | VPC¦Transit Gateway¦NAT Gateway | FIN-EPIC-COST-25 | efficiency | -3600 | 2026-01-11
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-113 | Schedule non-prod EKS clusters to scale to zero overnight | Dev and staging EKS clusters run 24x7 but get zero traffic 19:00-08:00. Use Karpenter scheduled scaling to drain to zero nodes overnight. | Story | To Do | Medium | 5 | j.alvarez@example.com | k.menon@example.com | finops¦efficiency¦eks | platform | EKS¦EC2 | FIN-EPIC-COST-25 | efficiency | -8800 | 2026-01-11
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-114 | Remove orphaned Elastic IPs (43 unattached) | Cost Explorer flags 43 unattached EIPs at $3.60/month each. Validate against asset DB, then release. | Task | Done | Low | 1 | r.patel@example.com | k.menon@example.com | finops¦cleanup | networking | EC2 | FIN-EPIC-COST-25 | cleanup | -160 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-115 | Snapshot lifecycle: expire EBS snapshots older than 90 days | We retain 11 months of EBS snapshots by default. DLM policy: expire daily snapshots after 14 days, weekly after 90 days. | Task | To Do | Low | 2 | n.oduya@example.com | k.menon@example.com | finops¦cleanup¦ebs | platform | EBS¦DLM | FIN-EPIC-COST-25 | cleanup | -1900 | 2026-01-11
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-116 | Deploy Cost Anomaly Detection alerts to Slack #finops | Wire AWS Cost Anomaly Detection alerts into Slack #finops with daily digest. Includes per-service threshold of $500/day deviation. | Story | To Do | Medium | 3 | k.menon@example.com | k.menon@example.com | finops¦observability | observability | Cost Explorer¦SNS | FIN-EPIC-COST-25 | cost_optimization | 50 | 2026-01-11
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-117 | Migrate dev databases from RDS to Aurora Serverless v2 | Dev RDS instances cost ~$2,800/month combined and idle 70 percent of the time. Move to Aurora Serverless v2 (min 0.5 ACU). | Story | To Do | Medium | 8 | s.huang@example.com | k.menon@example.com | finops¦rightsizing¦rds | data-platform | RDS¦Aurora Serverless v2 | FIN-EPIC-COST-25 | rightsizing | -1900 | 2026-01-11
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-118 | Patch CVE-2025-9911 in customer-portal base image | Critical CVE in OpenSSL base image. Bump to patched image and redeploy customer-portal. Tier-1 service; coordinate with on-call. | Bug | In Progress | Highest | 3 | a.kim@example.com | secops@example.com | security¦cve¦must-do | customer-portal | ECR¦EKS | SEC-EPIC-2026-Q1 | security | 0 | 2026-01-08
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-119 | Fix flaky checkout integration test on CI | checkout_e2e_smoke flakes ~20 percent of the time on PR builds. Root-causes to a timing assumption around Stripe sandbox latency. | Bug | In Progress | Medium | 2 | a.kim@example.com | j.alvarez@example.com | bug¦ci | checkout |  |  | bug_fixes | 0 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-120 | Document FinOps tagging standard in engineering wiki | Single page covering cost-center, owner, env, service tags. Linked from onboarding doc. | Task | To Do | Low | 1 | k.menon@example.com | k.menon@example.com | finops¦docs | platform |  | FIN-EPIC-COST-25 | efficiency | 0 | 2026-01-11
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-121 | Spike: evaluate AWS Compute Optimizer recommendations | Pull current Compute Optimizer recommendations for EC2, EBS, Lambda. Estimate annualized savings if accepted. | Spike | To Do | Medium | 3 | k.menon@example.com | k.menon@example.com | finops¦spike | platform | Compute Optimizer | FIN-EPIC-COST-25 | cost_optimization | 0 | 2026-01-11
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-122 | Patch on-call runbook: search-v1 decommission rollback | Add rollback steps to runbook for FIN-109. If anyone still calls search-v1 endpoint after teardown, point them at search-v2 alias. | Task | To Do | Low | 1 | r.patel@example.com | j.alvarez@example.com | docs¦runbook | search |  | FIN-EPIC-COST-25 | maintenance | 0 | 2026-01-12
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-123 | Bug: cost dashboard pulls stale CUR data on Mondays | FinOps cost dashboard widget shows last week's data on Mondays because CUR refresh job runs Sunday 23:50 UTC and frontend caches for 24h. Fix cache TTL. | Bug | To Do | Medium | 2 | n.oduya@example.com | k.menon@example.com | bug¦finops¦observability | observability | Cost Explorer¦QuickSight | FIN-EPIC-COST-25 | bug_fixes | 0 | 2026-01-12
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-124 | Enable IMDSv2 across remaining EC2 fleet (security) | 247 EC2 instances still on IMDSv1. Roll out IMDSv2-only via launch template update; coordinate restart windows with service owners. | Task | To Do | High | 5 | a.kim@example.com | secops@example.com | security¦ec2 | platform | EC2 | SEC-EPIC-2026-Q1 | security | 0 | 2026-01-09
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-125 | Rightsize Lambda memory for invoice-pdf-generator | Lambda Insights shows invoice-pdf-generator over-provisioned at 2048 MB; uses 380 MB p95. Drop to 768 MB and re-benchmark. | Story | To Do | Low | 2 | s.huang@example.com | k.menon@example.com | finops¦rightsizing¦lambda | billing | Lambda | FIN-EPIC-COST-25 | rightsizing | -640 | 2026-01-12
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-126 | Improve cost allocation report: per-team breakdown | Extend QuickSight cost dashboard with per-team breakdown using cost-center tag. Required by FinOps monthly review. | Story | To Do | Medium | 3 | n.oduya@example.com | k.menon@example.com | finops¦observability | observability | QuickSight | FIN-EPIC-COST-25 | observability | 0 | 2026-01-12
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-127 | Replace cron-on-EC2 reporting jobs with EventBridge + Lambda | Two t3.medium 'cron boxes' run nightly Python reports. Move to EventBridge schedules + Lambda; retire the EC2 instances. | Story | To Do | Low | 5 | j.alvarez@example.com | k.menon@example.com | finops¦cleanup¦serverless | data-platform | EC2¦EventBridge¦Lambda | FIN-EPIC-COST-25 | cleanup | -340 | 2026-01-12
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-128 | Fix bug: monthly Savings Plan utilization email broken | Lambda that emails monthly SP utilization report fails on >100 KB attachments. Switch to S3 presigned URL. | Bug | To Do | Low | 2 | n.oduya@example.com | k.menon@example.com | bug¦finops | observability | Lambda¦SES¦S3 | FIN-EPIC-COST-25 | bug_fixes | 0 | 2026-01-12
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-129 | Add small Karpenter consolidation policy on platform-prod | Enable Karpenter consolidation = WhenUnderutilized on platform-prod (already on staging). Reduces idle nodes during off-peak. | Story | To Do | Medium | 3 | j.alvarez@example.com | k.menon@example.com | finops¦efficiency¦eks | platform | EKS¦EC2 | FIN-EPIC-COST-25 | efficiency | -5200 | 2026-01-12
AWS-COST-OPT-2026 | 1 | Sprint 1 - Cost Optimization Kickoff | 2026-01-12 | 2026-01-23 | FIN-130 | Add p99 latency SLO check to rightsizing rollout playbook | Guardrail: every rightsizing PR must include before/after p99 latency from CloudWatch. Add CI check + reviewer template. | Task | To Do | High | 3 | j.alvarez@example.com | k.menon@example.com | finops¦reliability¦guardrail | platform | CloudWatch | FIN-EPIC-COST-25 | reliability | 0 | 2026-01-12