## sprint_3
project_id | sprint_number | sprint_name | sprint_start | sprint_end | ticket_id | title | description | type | status | priority | story_points | assignee | reporter | labels | components | aws_services | epic_link | ground_truth_theme | estimated_monthly_impact_usd | created_at
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-301 | Scale EKS payments-prod node group +60 percent (post-promo retained) | Marketing kept the promo CTA after the event. Lock in node group at 80 m5.4xlarge instead of scaling back. | Story | In Progress | Highest | 5 | j.alvarez@example.com | p.lopez@example.com | scaling¦capacity¦eks | payments | EKS¦EC2 | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 41000 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-302 | Add 3 more Aurora read replicas for checkout-prod | Sustained read load from new gift cards / BNPL flows. Add 3 r6g.4xlarge readers. | Story | To Do | Highest | 5 | s.huang@example.com | p.lopez@example.com | scaling¦capacity¦aurora | checkout | RDS Aurora | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 14400 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-303 | Add 6 Kafka brokers to events-prod | Sustain higher throughput for new analytics pipelines from gift cards + BNPL features. | Story | To Do | High | 8 | j.alvarez@example.com | p.lopez@example.com | scaling¦kafka¦capacity | events | MSK | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 11000 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-304 | Stand up new EKS cluster in eu-central-1 | Bring up production EKS cluster eu-prod-eks for EU expansion. | Epic | In Progress | Highest | 13 | j.alvarez@example.com | p.lopez@example.com | expansion¦geo¦eks | platform | EKS¦EC2 | GROWTH-EPIC-2026-Q1 | expansion | 38000 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-305 | Provision Aurora Global Database (us-east-1 -> eu-central-1) | Create Aurora Global Database for EU read replicas. | Story | To Do | Highest | 8 | s.huang@example.com | p.lopez@example.com | expansion¦geo¦aurora | data-platform | RDS Aurora | GROWTH-EPIC-2026-Q1 | expansion | 27000 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-306 | Deploy CloudFront EU edge presence | Add EU edge locations and origin failover for eu-prod stack. | Story | To Do | High | 5 | n.oduya@example.com | p.lopez@example.com | expansion¦geo¦cdn | edge | CloudFront | GROWTH-EPIC-2026-Q1 | expansion | 6800 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-307 | Replicate S3 product-images bucket to eu-central-1 | Cross-region replication for product-images bucket (12 TB) into eu-central-1. | Story | To Do | High | 5 | r.patel@example.com | p.lopez@example.com | expansion¦geo¦s3 | media | S3 | GROWTH-EPIC-2026-Q1 | expansion | 4400 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-308 | New feature: subscriptions module | Net-new recurring subscriptions module: API, billing scheduler, webhooks. Multiple new Lambdas + new DynamoDB tables. | Epic | To Do | High | 21 | p.lopez@example.com | product@example.com | feature¦billing | billing | Lambda¦DynamoDB¦EventBridge | GROWTH-EPIC-2026-Q1 | feature_development | 3200 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-309 | New feature: loyalty points engine | Net-new loyalty points engine with rules DSL. New Lambdas + DynamoDB stream consumer. | Epic | To Do | High | 21 | p.lopez@example.com | product@example.com | feature¦loyalty | loyalty | Lambda¦DynamoDB¦Kinesis | GROWTH-EPIC-2026-Q1 | feature_development | 2700 | 2026-02-05
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-310 | Increase ElastiCache cluster size from 4 to 8 nodes | Promo retention added sustained traffic. Permanently scale ElastiCache from 4 to 8 cache.r6g.xlarge nodes. | Story | To Do | High | 3 | s.huang@example.com | p.lopez@example.com | scaling¦capacity¦cache | platform | ElastiCache | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 6800 | 2026-02-06
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-311 | Increase DynamoDB on-demand on orders-prod (post-promo retained) | Switch orders-prod to on-demand at sustained higher level after promo. | Task | To Do | High | 2 | s.huang@example.com | p.lopez@example.com | scaling¦capacity¦dynamodb | orders | DynamoDB | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 9200 | 2026-02-06
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-312 | Pre-provision OpenSearch capacity for EU launch | Stand up 9-node OpenSearch cluster in eu-central-1 to back EU search. | Story | To Do | High | 8 | r.patel@example.com | p.lopez@example.com | expansion¦geo¦opensearch | search | OpenSearch | GROWTH-EPIC-2026-Q1 | expansion | 18000 | 2026-02-06
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-313 | Stand up Kinesis ingestion in eu-central-1 | Provision Kinesis Data Streams in eu-central-1 for cross-region event mirroring. | Story | To Do | High | 5 | j.alvarez@example.com | p.lopez@example.com | expansion¦geo¦kinesis | events | Kinesis | GROWTH-EPIC-2026-Q1 | expansion | 5200 | 2026-02-06
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-314 | Add 2 more brokers to logging Kafka cluster | Logging cluster lag spiking; add 2 m5.large brokers. | Task | To Do | Medium | 3 | n.oduya@example.com | j.alvarez@example.com | scaling¦kafka¦observability | observability | MSK | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 3600 | 2026-02-06
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-315 | New feature: gift cards EU rollout | Localize gift cards module for EU (currency, VAT, language). | Story | To Do | High | 8 | p.lopez@example.com | product@example.com | feature¦geo | checkout | Lambda¦DynamoDB | GROWTH-EPIC-2026-Q1 | feature_development | 1800 | 2026-02-06
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-316 | Pre-provision ALB capacity in eu-central-1 | Pre-warm ALBs in eu-central-1 ahead of EU go-live. | Task | To Do | High | 2 | n.oduya@example.com | p.lopez@example.com | expansion¦geo¦alb | networking | ALB | GROWTH-EPIC-2026-Q1 | expansion | 1400 | 2026-02-07
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-317 | Maintenance: Aurora minor version upgrade across prod | Routine Aurora minor version upgrade. Required for support coverage. | Task | To Do | Medium | 3 | s.huang@example.com | j.alvarez@example.com | maintenance¦rds | data-platform | RDS Aurora |  | maintenance | 0 | 2026-02-07
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-318 | Patch CVE-2026-2210 in Java base image | Critical Spring CVE; rebuild Java base image and redeploy 18 services. | Bug | In Progress | Highest | 5 | a.kim@example.com | secops@example.com | security¦cve | platform | ECR¦EKS | SEC-EPIC-2026-Q1 | security | 0 | 2026-02-04
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-319 | Reliability: gameday for EU failback to us-east-1 | Gameday for failing EU traffic back to us-east-1 if eu-central-1 degrades. | Task | To Do | Medium | 5 | a.kim@example.com | j.alvarez@example.com | reliability¦gameday¦geo | platform | Route53¦EKS | GROWTH-EPIC-2026-Q1 | reliability | 0 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-320 | Bug: Aurora Global writeback latency spikes during failover test | Investigate and fix writeback latency during multi-region failover. | Bug | To Do | High | 5 | s.huang@example.com | a.kim@example.com | bug¦aurora | data-platform | RDS Aurora |  | bug_fixes | 0 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-321 | Observability: add EU dashboards to Datadog | Mirror existing US dashboards for the EU stack. | Task | To Do | Medium | 3 | n.oduya@example.com | j.alvarez@example.com | observability¦geo | observability | CloudWatch | GROWTH-EPIC-2026-Q1 | observability | 600 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-322 | Maintenance: rotate KMS keys per quarterly policy | Quarterly KMS key rotation across prod accounts. | Task | To Do | Low | 2 | a.kim@example.com | secops@example.com | maintenance¦security | platform | KMS |  | maintenance | 0 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-323 | Continue Graviton rollout (search-prod, 50 percent canary) | Follow-on to FIN-110 / FIN-201. Roll search-prod to 50 percent Graviton. | Story | To Do | Medium | 5 | j.alvarez@example.com | k.menon@example.com | finops¦rightsizing¦graviton | search | EC2¦EKS | FIN-EPIC-COST-25 | rightsizing | -6200 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-324 | Cleanup: old NAT Gateway in retired sandbox VPC | Sandbox VPC retired; NAT Gateway still alive. Remove. | Task | To Do | Low | 1 | r.patel@example.com | k.menon@example.com | finops¦cleanup¦networking | networking | VPC¦NAT Gateway | FIN-EPIC-COST-25 | cleanup | -150 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-325 | Apply S3 lifecycle to EU product-images bucket | Mirror US lifecycle policy to EU bucket so we don't repeat the mistake. | Task | To Do | Low | 2 | n.oduya@example.com | k.menon@example.com | finops¦s3¦efficiency¦geo | media | S3 | FIN-EPIC-COST-25 | efficiency | -800 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-326 | New feature: loyalty points UI in mobile app | Mobile UI for loyalty points (paired with FIN-309). | Story | To Do | Medium | 8 | p.lopez@example.com | product@example.com | feature¦mobile | mobile | AppSync¦Cognito | GROWTH-EPIC-2026-Q1 | feature_development | 900 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-327 | Increase Lambda concurrency limit on checkout-tokenize | Raise reserved concurrency from 200 to 600 for the new BNPL flow. | Task | To Do | High | 1 | p.lopez@example.com | p.lopez@example.com | scaling¦capacity¦lambda | checkout | Lambda | GROWTH-EPIC-2026-Q1 | infrastructure_scaling | 1100 | 2026-02-08
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-328 | Stand up dedicated bastion in eu-central-1 | Bastion host + SSO for EU stack ops access. | Task | To Do | Medium | 2 | a.kim@example.com | p.lopez@example.com | expansion¦geo¦security | platform | EC2¦SSO | GROWTH-EPIC-2026-Q1 | expansion | 280 | 2026-02-09
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-329 | Bug: cost dashboard misclassifies eu-central-1 spend as 'untagged' | EU resources lack the cost-center tag because the new region launch skipped the SCP. Fix tagging at provisioning. | Bug | To Do | Medium | 3 | n.oduya@example.com | k.menon@example.com | bug¦finops¦geo | platform | IAM¦Cost Explorer | FIN-EPIC-COST-25 | bug_fixes | 0 | 2026-02-09
AWS-COST-OPT-2026 | 3 | Sprint 3 - Promo Capacity & New Region | 2026-02-09 | 2026-02-20 | FIN-330 | Decommission old promo-prep capacity in non-prod | Tear down promo-prep oversize node groups in staging that were used for load tests. | Task | To Do | Low | 2 | r.patel@example.com | k.menon@example.com | finops¦cleanup¦eks | platform | EKS¦EC2 | FIN-EPIC-COST-25 | cleanup | -2200 | 2026-02-09